## Sheet1
Task | Hours | Progress
Project and dependency upgrades (compile with latest SDK) | 4 | 80%
SQLite database for offline maps
Design | 2 | 60%
Entity objects | 3 | 60%
DAO objects | 3 | 60%
Backend API integration
Requesting offline map | 4 | 80%
Downloading offline map package with progress indication | 4 | 80%
Processing offline map package and storing locally | 4 | 80%
Uploading offline changes | 4 | 0%
Offline map switching | 2 | 80%
Offline switching between multiple active layers | 4 | 0%
Offline feature selection
Points | 3 | 0%
Lines | 4 | 0%
Polygons | 6 | 0%
Offline changes queue or flagging mechanism | 16 | 0%
Raster tiles rendering | 4 | 80%
Vector layers rendering
Points | 4 | 60%
Lines | 6 | 60%
Polygons | 8 | 60%
Offline styling
Points | 2 | 80%
Lines | 3 | 80%
Polygons | 4 | 80%
Offline info view
Basic view | 2 | 0%
Grouped view | 4 | 0%
Offline attributes editing
Basic view | 4 | 0%
Grouped view | 6 | 0%
Offline spatial editing
Add Point | 2 | 0%
Add Line | 4 | 0%
Add Polygon | 4 | 0%
Edit Point | 2 | 0%
Edit Line | 4 | 0%
Edit Polygon | 4 | 0%
Delete Point | 2 | 0%
Delete Line | 2 | 0%
Delete Polygon | 2 | 0%
Tile caching | 4 | 0%
Offline data grid
View | 4 | 0%
Selection | 2 | 0%
Searching | 4 | 0%
Filtering | 4 | 0%
Offline map filtering | 4 | 0%
Disabling certain functionality during offline | 3 | 0%
QA and testing
Android testing | 3 | 0%
iOS testing | 3 | 0%
Huawei testing | 3 | 0%
Deployment
Apple App Store | 4 | 0%
Google Play Store | 2 | 0%
Huawei App Gallery | 2 | 0%
Total | 178